## Sheet1
CSI4142 - Project W23
Phase 2- Physical design and data staging
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Create database instance | Fatimetou, Othniel, Opemipo | 2023-03-22 | 2023-03-24 | 4 hours | 5 hours | Had to make sure that our sources were reliable and our instances were accurate. Also, that our loaded dataset was making sense
Create <all listed in Schema> dimension | Opemipo | 2023-03-15 | 2023-03-15 | 2 hours | 3 hours
Staging of dimension <all listed in Schema> | Othniel | 2023-03-17 | 2023-03-17 | 4 hours | 3 hours
Surrogate key pipeline | Fatimetou | 2023-03-20 | 2023-03-20 | 3 hours | 2 hours
Staging of fact table – including FKs and measures | Fatimetou, Othniel, Opemipo | 2023-03-20 | 2023-03-22 | 3 hours | 5 hours | Took more time because we kept running into errors and had to deal with them first
Data quality handling and reporting | Fatimetou, Othniel, Opemipo | 2023-03-22 | 2023-03-24 | 4 hours | 5 hours | Took more time because we kept running into errors and had to deal with them first
Others – if any